## Sheet1
| Project Start : | 9/13/2022
| Display Week : | 1 |  | sep 13 - sep 19 | [6 empty] | sep20 - sep 26 | [6 empty] | sep 27 - oct 3 | [6 empty] | oct 4 - oct 10 | [6 empty] | oct 11 - oct 17 | [6 empty] | 0ct 18 - oct 24 | [6 empty] | oct 28-0ct 31 | [6 empty] | nov 1-nov 7 | [6 empty] | nov 8- nov14 | [6 empty] | nov 15-nov21 | [6 empty] | nov 22-nov 28
TASK |  | START | END | 13 | 14 | 15 | 16 | 18 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 34 | 25 | 26 | 27 | 28
1. Planning |  | 9/13/2022 | 9/19/2022
Project idea
IDE, Language, tools decision
Gathering skill set
Assigning team member roles
Risk Management
2. Requirement Eliciation |  | 9/20/2022 | 2022-10-10
Gathering requirements
System Specifications
Feasability study
3. Designing |  | 2022-11-10 | 10/20/2022
Identifying features
Framing of Interfaces
Flow Cart and activity diagram
Check for database required pages
Listing of the database fileds
Designing a database model
4. Implementation |  | 10/21/2022 | 2022-07-11
Design interfaces
Webpages creation
Integration with javascript
Creating tables in database
Inspect the code for improvements
Integration of front - end- with backend
5. Testing |  | 2022-08-11 | 11/20/2022
Checking features
identifying bugs in data
Framing test cases
Failure check
6. Maintainence |  | 11/21/2022 | 11/28/2022
Making changes and adjusting the project
Preparing the final report